## Task List
ID | Phase | Task | Start Date | End Date | Duration (days) | Notes / Dependencies | Offset (days) | Project start | 2026-08-27
1 | P0: Kickoff | Build & submit Gantt chart | 2026-08-27 | 2026-09-02 | 7 | Due to professor next week | 0 | Project end | 2026-12-31
2 | P0: Kickoff | Start SRS draft (intro, scope, purpose) | 2026-08-27 | 2026-09-02 | 7 |  | 0 | Total days | 127
3 | P0: Kickoff | Finish Computer Vision & Speech-to-Text course | 2026-08-27 | 2026-09-02 | 7 | Coursera | 0 | Total tasks | 34
4 | P0: Kickoff | Finish Agentic AI / LLM / RAG self-study | 2026-08-27 | 2026-09-02 | 7 |  | 0
5 | P0: Kickoff | Requirement gathering & competitor research | 2026-08-27 | 2026-09-02 | 7 |  | 0
6 | P0: Kickoff | AI Demos | 2026-08-27 | 2026-09-02 | 7 |  | 0
7 | P0: Kickoff | Login-Signup-OTP-Home Pages UI (simple)(Figma) | 2026-08-27 | 2026-09-02 | 7 |  | 0
8 | P0: Kickoff | Documentation | 2026-08-27 | 2026-09-02 | 7 |  | 0
9 | P0: Kickoff | Diagrams Research | 2026-08-27 | 2026-09-02 | 7 |  | 0
10 | P0: Kickoff | Brand identity | 2026-08-27 | 2026-09-02 | 7 |  | 0
11 | P1: Research & Requirements | SRS - Functional requirements | 2026-09-03 | 2026-09-16 | 14 | Recovered from Sheet1 | 7
12 | P1: Research & Requirements | SRS - Non-functional requirements | 2026-09-08 | 2026-09-16 | 9 | Recovered from Sheet1 | 12
13 | P1: Research & Requirements | Define user personas | 2026-09-08 | 2026-09-16 | 9 | Recovered from Sheet1 | 12
14 | P2: Design & Architecture | High-fidelity UI/UX design (Figma) | 2026-09-17 | 2026-10-01 | 15 | Recovered from Sheet1 | 21
15 | P2: Design & Architecture | Use cases & user scenarios document | 2026-09-17 | 2026-09-28 | 12 |  | 21
16 | P2: Design & Architecture | Exception handling documentation | 2026-09-22 | 2026-10-01 | 10 |  | 26
17 | P2: Design & Architecture | System architecture design | 2026-09-17 | 2026-09-30 | 14 | Frontend/backend/AI agents/DB | 21
18 | P2: Design & Architecture | Tech stack finalization | 2026-09-17 | 2026-09-21 | 5 |  | 21
19 | P3: Core Build Sprint 1 | Frontend scaffolding (pages, nav, auth) | 2026-10-08 | 2026-10-21 | 14 | Angular/React | 42
20 | P3: Core Build Sprint 1 | Backend setup + database schema | 2026-10-08 | 2026-10-21 | 14 |  | 42
21 | P3: Core Build Sprint 1 | Receipt upload feature + basic OCR | 2026-10-15 | 2026-11-04 | 21 |  | 49
22 | P3: Core Build Sprint 1 | Bank/transaction integration (research + v1) | 2026-10-15 | 2026-11-04 | 21 |  | 49
23 | P4: AI Agent Integration Sprint 2 | Agentic AI decision-support assistant | 2026-11-05 | 2026-11-25 | 21 |  | 70
24 | P4: AI Agent Integration Sprint 2 | RAG for financial insights | 2026-11-05 | 2026-11-25 | 21 |  | 70
25 | P4: AI Agent Integration Sprint 2 | Speech-to-text feature integration | 2026-11-05 | 2026-11-18 | 14 |  | 70
26 | P4: AI Agent Integration Sprint 2 | Computer vision refinement for receipts | 2026-11-05 | 2026-11-18 | 14 |  | 70
27 | P4: AI Agent Integration Sprint 2 | Multimodal agent orchestration (demo-ready) | 2026-11-18 | 2026-12-02 | 15 | Agents callable inside demo | 83
28 | P5: Testing & Polish | Integration testing | 2026-12-03 | 2026-12-09 | 7 |  | 98
29 | P5: Testing & Polish | Exception handling implementation | 2026-12-03 | 2026-12-12 | 10 |  | 98
30 | P5: Testing & Polish | Bug fixes & UI polish | 2026-12-08 | 2026-12-16 | 9 |  | 103
31 | P6: Thesis, Presentation & Demo | Finalize thesis document | 2026-12-17 | 2026-12-27 | 11 |  | 112
32 | P6: Thesis, Presentation & Demo | Build presentation slides | 2026-12-17 | 2026-12-24 | 8 |  | 112
33 | P6: Thesis, Presentation & Demo | Rehearse demo | 2026-12-24 | 2026-12-30 | 7 |  | 119
34 | P6: Thesis, Presentation & Demo | Final submission | 2026-12-31 | 2026-12-31 | 1 |  | 126
HOW TO USE
Edit only the shaded Start Date and End Date cells. Duration and Offset recalculate.
Offset is a helper column. It is the days each task waits after the project start, and it drives the invisible spacer bar in the chart.
If you change the earliest start date, reset the chart axis maximum on the Gantt Chart tab to match Total days in K3.
Tasks marked Recovered from Sheet1 were missing from this tab. Sheet1 has been left untouched as your earlier draft.

## Sheet1
ID | Phase | Task | Start Date | End Date | Duration (days) | Notes / Dependencies
1 | P0: Kickoff | Build & submit Gantt chart | 2026-08-27 | 2026-09-02 | 7 | Due to professor next week
2 | P0: Kickoff | Start SRS draft (intro, scope, purpose) | 2026-08-27 | 2026-09-02 | 7
3 | P0: Kickoff | Finish Computer Vision & Speech-to-Text course | 2026-08-27 | 2026-09-02 | 7 | Coursera
4 | P0: Kickoff | Finish Agentic AI / LLM / RAG self-study | 2026-08-27 | 2026-09-02 | 7
5 | P0: Kickoff | Requirement gathering & competitor research | 2026-08-27 | 2026-09-02 | 7
6 | P0: Kickoff | AI Demos | 2026-08-27 | 2026-09-02 | 7
7 | P0: Kickoff | Login-Signup-OTP-Home Pages UI (simple)(Figma) | 2026-08-27 | 2026-09-02 | 7
8 | P0: Kickoff | Documentation | 2026-08-27 | 2026-09-02 | 7
9 | P0: Kickoff | Diagrams Research | 2026-08-27 | 2026-09-02 | 7
10 | P0: Kickoff | Brand identity | 2026-08-27 | 2026-09-02 | 7
11 | P1: Research & Requirements | SRS - Functional requirements | 2026-09-03 | 2026-09-16 | 14
12 | P1: Research & Requirements | SRS - Non-functional requirements | 2026-09-08 | 2026-09-16 | 9
13 | P1: Research & Requirements | Define user personas | 2026-09-08 | 2026-09-16 | 9
14 | P2: Design & Architecture | High-fidelity UI/UX design (Figma) | 2026-09-17 | 2026-10-01 | 15
15 | P2: Design & Architecture | Use cases & user scenarios document | 2026-09-17 | 2026-09-28 | 12
16 | P2: Design & Architecture | Exception handling documentation | 2026-09-22 | 2026-10-01 | 10
17 | P2: Design & Architecture | System architecture design | 2026-09-17 | 2026-09-30 | 14 | Frontend/backend/AI agents/DB
18 | P2: Design & Architecture | Tech stack finalization | 2026-09-17 | 2026-09-21 | 5

## Gantt Chart
Phase Legend
P0: Kickoff
P1: Research & Requirements
P2: Design & Architecture
P3: Core Build Sprint 1
P4: AI Agent Integration Sprint 2
P5: Testing & Polish
P6: Thesis, Presentation & Demo