## Task List
ID | Phase | Task | Type | Feature Name / Description | Start Date | End Date | Duration (days) | Depends on (ID) | Notes | Within deadline? | AI (days) | Normal (days) | Thesis (days) | General (days) | Project start | 2026-10-13
1 | P1: Setup | MVP scope freeze & architecture | General |  | 2026-10-13 | 2026-10-18 | 6 |  |  | OK | 0 | 0 | 0 | 6 | Project end | 2026-12-31
2 | P2: AI Core | AI foundation (models, data, pipeline) | AI |  | 2026-10-13 | 2026-11-01 | 20 |  | The 3 AI features wait for this | OK | 20 | 0 | 0 | 0 | Deadline | 2026-12-31
3 | P3: MVP Features | Feature 1 | AI |  | 2026-11-02 | 2026-11-22 | 21 | 2 | AI-dependent | OK | 21 | 0 | 0 | 0 | Total days | 80
4 | P3: MVP Features | Feature 2 | AI |  | 2026-11-09 | 2026-11-29 | 21 | 2 | AI-dependent | OK | 21 | 0 | 0 | 0 | Days of slack | 0
5 | P3: MVP Features | Feature 3 | AI |  | 2026-11-16 | 2026-12-06 | 21 | 2 | AI-dependent | OK | 21 | 0 | 0 | 0 | MVP features | 5
6 | P3: MVP Features | Feature 4 | Normal |  | 2026-10-19 | 2026-11-08 | 21 | 1 | No AI dependency | OK | 0 | 21 | 0 | 0 | AI-dependent features | 3
7 | P3: MVP Features | Feature 5 | Normal |  | 2026-11-02 | 2026-11-22 | 21 | 1 | No AI dependency | OK | 0 | 21 | 0 | 0 | Schedule status | ON TRACK
8 | P4: Testing | Integration & testing | General |  | 2026-12-07 | 2026-12-16 | 10 | 3,4,5,6,7 |  | OK | 0 | 0 | 0 | 10
9 | P4: Testing | Bug fixes & polish | General |  | 2026-12-12 | 2026-12-20 | 9 | 8 |  | OK | 0 | 0 | 0 | 9
10 | P5: Thesis | Thesis - write chapters | Thesis |  | 2026-10-26 | 2026-12-13 | 49 |  | Runs in parallel with the build | OK | 0 | 0 | 49 | 0
11 | P5: Thesis | Thesis - review & finalize | Thesis |  | 2026-12-14 | 2026-12-27 | 14 | 10 |  | OK | 0 | 0 | 14 | 0
12 | P6: Delivery | Presentation & demo rehearsal | General |  | 2026-12-21 | 2026-12-29 | 9 | 9 |  | OK | 0 | 0 | 0 | 9
13 | P6: Delivery | Final submission | General |  | 2026-12-30 | 2026-12-31 | 2 | 11,12 | Hard deadline: end of month 12 | OK | 0 | 0 | 0 | 2
HOW TO USE
Yellow cells: type the name / description of each feature. They are left empty on purpose.
Blue shaded cells: Start Date, End Date and the Deadline are the only cells to edit. Everything else recalculates.
Type drives the bar colour in the chart: AI = AI-dependent, Normal = no AI dependency, Thesis, General.
Features 1-3 are AI-dependent and start only after task 2 (AI foundation) ends. Features 4-5 are normal and start right after setup.
Columns M-P are chart helpers. Do not edit them.
If you move the earliest start or the deadline, update the date axis min/max on the Gantt Chart tab (currently 09-Oct-2026 to 01-Jan-2027).
Note on F2: Dates are a proposed schedule starting 13-Oct-2026. Edit freely.
Note on S3: Deadline given by the team: end of month 12 (31-Dec-2026).